## Sheet1
Category | Task | Approx time budgetn(hr) | Frequency | Seasonal Manager | Intern | Volunteer Coordinator | Communications
Pull Events | Schedule Events based on Partner group availablitiy | 2 | One Time | 2
Pull Events | Adjust schedule for weather and river conditions | 0.5 | week | 10
Pull Events/Education/Monitoring | Develop initial volunteer recruiting and edcuational materials | 2 | One Time | 2 |  | X | X
Pull Events/Monitoring | Distribute volunteer recruiting and educational materials to approprate outlets | 1 | week |  |  | x | x
Pull Events | Staff events (manage volunteers, ensure that waivers have been signed, hand out supplies, assist volunteers with boats, ensure that required data is documented) | 6 | WEEK | 120 | 120
Data collection | Develop and maintain tracking system for volunteers, harvest amounts and monitoring reports | 0.5 | week | 10 | 10
Surveys | Survey when needed in order to develop pull strategy for events or to fill volunteer monitoring gaps | 2 | week |  | 40
Pull Events | Event preparation: Develop strategy for each pull event in order to ensure that priority areas are a focus at each pull and develop and print maps for the event, get supplies | 1 | week | 10 | 20
Pull Events | Post event tasks - clean boat, wash and dry gloves store supplies properly | 1 | week |  | 20
Pull Events | Update pull event information as needed | 0.5 | week |  | 10 | x | x
Monitoring | Check for new reports to EpiCollect and contact volunteer monitors if needed | 1 | week |  | 20
Education | Develop media outreach for public education and send to local media oulets | 0.5 | week | 10 | 10 | x | x
Pull events/monitoring/education | Respond to phone and email inquiries and correspond and coordinate with project partners | 1 | week | 20 | 20
Management | Ensure that all aspects of the program are being carried out appropriately and handle management issues as they arise | 1 | week | 20 | 20
Management | Prepare and distribute an end of season report | 2 | one time | 2 | 40
Monitoring | Transfer Epicollect informaton to maps and keep maps updated | 1 | week |  | 20
| Total hours per season |  |  | 206 | 350
| Hours per week |  |  | 10.3 | 17.5